## Sheet1
Office Moving Checklist
Lease Expiration Date: |  |  |  | 2019-01-01
(mm/dd/yy)
Preparing to move your office or business can be a daunting task and a challenge for anyone; the key to success is preparation. There are many components that
need to be planed and managed prior to the moving truck arriving on move day. Use this office move checklist as a guide to keep you organized and
on track and break the complex process down into manageable stages. Assign a Task Owner, meet regularly with your move team to ensure that you
are on track for a succesfully, executed office relocation.
30 |  |  | Please call Kevin Stringer with any questions at (916) 275-4447 or email at kstringer@chipmanrelo.com
MONTHS |  | CATEGORY | TASK START | PREPARATION TASKS | TARGET COMPLETION | TASK OWNER | TASK COMPLETED
18 | 540 | Proj. Mgmt | 2017-07-10 | Move timeline and project schedule | 2019-01-01
18 | 540 | Proj. Mgmt | 2017-07-10 | Employee census and occupancy review | 2019-01-01
18 | 540 | Proj. Mgmt | 2017-07-10 | Site survey and facility review of current and proposed locations | 2019-01-01
18 | 540 | Proj. Mgmt | 2017-07-10 | Desired square footage needed at new location | 2019-01-01
18 | 540 | Proj. Mgmt | 2017-07-10 | Floor plan for new space that identifies work stations, equipment centers, offices, conference room needs, fixtures, and other support spaces | 2019-01-01
18 | 540 | Proj. Mgmt | 2017-07-10 | Architect for new construction, upgrades and/or buildouts | 2019-01-01
18 | 540 | Proj. Mgmt | 2017-07-10 | Office relocation budget | 2019-01-01
12 | 360 | Technology | 2018-01-06 | IT infrastructure assessment of current and proposed locations | 2019-01-01
12 | 360 | Technology | 2018-01-06 | Inventory of all technology assets | 2019-01-01
12 | 360 | Technology | 2018-01-06 | Evaluation of current cabling and network via industry best practices | 2019-01-01
12 | 360 | Technology | 2018-01-06 | Evaluation of technology upgrades for potential project consolidation | 2019-01-01
12 | 360 | Technology | 2018-01-06 | Inventory of critical business and support applications | 2019-01-01
12 | 360 | Technology | 2018-01-06 | Evaluation of network downtime options versus redundant hardware and applications during cut over | 2019-01-01
6 | 180 | Technology | 2018-07-05 | Desktop relocation support strategy and resources | 2019-01-01
6 | 180 | Technology | 2018-07-05 | Evaluation of power, AC, ventilation, network and equipment positioning requirements | 2019-01-01
6 | 180 | Furniture | 2018-07-05 | Furniture selection criteria and specifications | 2019-01-01
10 | 300 | Furniture | 2018-03-07 | Comprehensive furniture inventory | 2019-01-01
10 | 300 | Furniture | 2018-03-07 | Evaluation of furniture options: | 2019-01-01
10 | 300 | Furniture | 2018-03-07 | Reuse existing furniture | 2019-01-01
10 | 300 | Furniture | 2018-03-07 | Repurpose existing furniture | 2019-01-01
10 | 300 | Furniture | 2018-03-07 | Purchase new furniture | 2019-01-01
10 | 300 | Furniture | 2018-03-07 | Purchase refurbished options | 2019-01-01
5 | 150 | Furniture | 2018-08-04 | Sell/decommission old furniture | 2019-01-01
12 | 360 | Telecom | 2018-01-06 | Evaluation of phone system: order new or relocate existing | 2019-01-01
9 | 270 | Telecom | 2018-04-06 | Phone numbers: order new or transfer existing through carrier | 2019-01-01
9 | 270 | Telecom | 2018-04-06 | Data services: order new or transfer existing (POTS, T‐1, ISDN, DSL) | 2019-01-01
6 | 180 | Docu Mgmt | 2018-07-05 | Secure off‐site storage needs | 2019-01-01
6 | 180 | Docu Mgmt | 2018-07-05 | Plan for on‐site storage needs | 2019-01-01
10 | 300 | Docu Mgmt | 2018-03-07 | Update filing requirements for employees | 2019-01-01
6 | 180 | Docu Mgmt | 2018-07-05 | Determine filing space for departments | 2019-01-01
6 | 180 | Docu Mgmt | 2018-07-05 | Document destruction: select or notify vendor of new location | 2019-01-01
6 | 180 | Docu Mgmt | 2018-07-05 | Dispose of or archive old files (consider sensitive documents) | 2019-01-01
6 | 180 | Communication | 2018-07-05 | Internal communications plan for employees | 2019-01-01
6 | 180 | Communication | 2018-07-05 | New building rules | 2019-01-01
6 | 180 | Communication | 2018-07-05 | Parking procedures | 2019-01-01
3 | 90 | Communication | 2018-10-03 | Move dates | 2019-01-01
2 | 60 | Communication | 2018-11-02 | Move and packing procedures | 2019-01-01
6 | 180 | Communication | 2018-07-05 | Network outage and contingency plan | 2019-01-01
2 | 60 | Communication | 2018-11-02 | Revise telephone and fax numbers | 2019-01-01
2 | 60 | Communication | 2018-11-02 | Required HR postings | 2019-01-01
6 | 180 | Communication | 2018-07-05 | External communications plan for customers, suppliers, service/utility providers and other pertinent vendors (e.g. accountant, attorney, insurance agent, etc.) | 2019-01-01
4 | 120 | Communication | 2018-09-03 | New address and phone numbers | 2019-01-01
4 | 120 | Communication | 2018-09-03 | Stationery and business cards | 2019-01-01
6 | 180 | Communication | 2018-07-05 | Building signage | 2019-01-01
6 | 180 | Communication | 2018-07-05 | Vehicle signage | 2019-01-01
6 | 180 | Communication | 2018-07-05 | Vehicle registrations | 2019-01-01
2 | 60 | Communication | 2018-11-02 | Update website and collateral to reflect new information | 2019-01-01
2 | 60 | Communication | 2018-11-02 | Revise advertising (including Yellow Pages and other directories) | 2019-01-01
1 | 30 | Communication | 2018-12-02 | Notify post office | 2019-01-01
3 | 90 | Communication | 2018-10-03 | Message scripts for communicating with external constituents | 2019-01-01
12 | 360 | Move | 2018-01-06 | Select department move coordinators | 2019-01-01
3 | 90 | Move | 2018-10-03 | Identify building restrictions for move hours | 2019-01-01
3 | 90 | Move | 2018-10-03 | Schedule elevator access at origin and destination | 2019-01-01
3 | 90 | Move | 2018-10-03 | Schedule parking and unloading at new site | 2019-01-01
3 | 90 | Move | 2018-10-03 | Obtain any special moving and/or parking permits | 2019-01-01
4 | 120 | Move | 2018-09-03 | IT staff onsite during the disconnect and reconnect of servers and data centers or consider outside support | 2019-01-01
3 | 90 | Move | 2018-10-03 | Arrange to have sensitive items packed and moved | 2019-01-01
3 | 90 | Move | 2018-10-03 | Computers | 2019-01-01
3 | 90 | Move | 2018-10-03 | Telephone equipment | 2019-01-01
3 | 90 | Move | 2018-10-03 | Networking equipment and servers | 2019-01-01
4 | 120 | Move | 2018-09-03 | Seating assignments at new location | 2019-01-01
2 | 60 | Move | 2018-11-02 | Packing needs for employees | 2019-01-01
2 | 60 | Move | 2018-11-02 | Common area packing requirements | 2019-01-01
4 | 120 | Move | 2018-09-03 | Plan for protection of confidential information | 2019-01-01
3 | 90 | Move | 2018-10-03 | Packing schedule: determine what can be packed in advance vs. last minute so your business can continue to operate as efficiently as possible with the least amount of interruption | 2019-01-01
1 | 30 | Move | 2018-12-02 | Communicate packing/labeling guidelines – professional movers will provide custom packing instructions and labels | 2019-01-01
1 | 30 | Move | 2018-12-02 | Packing supplies: ask your mover about crate rental vs. corrugated material – saves time, money and is better for the environment | 2019-01-01
0.5 | 15 | Move | 2018-12-17 | Ensure boxes or containers are properly packed and labeled with office location or name, importance, and contents | 2019-01-01
0.1 | 3 | Move | 2018-12-29 | Protection of floors, walls and elevators | 2019-01-01
6 | 180 | Security | 2018-07-05 | Master employee roster and access levels | 2019-01-01
6 | 180 | Security | 2018-07-05 | List of specialty areas that require restricted access | 2019-01-01
12 | 360 | Security | 2018-01-06 | List of areas that require enhanced fire suppression | 2019-01-01
9 | 270 | Security | 2018-04-06 | Monitoring services for employees and new facility | 2019-01-01
6 | 180 | Security | 2018-07-05 | Security system: select or transfer existing monitoring services | 2019-01-01
6 | 180 | Security | 2018-07-05 | Security plan for vacated space until turnover | 2019-01-01
6 | 180 | Vendors | 2018-07-05 | Moving | 2019-01-01
12 | 360 | Vendors | 2018-01-06 | Furniture installation/reconfiguration | 2019-01-01
18 | 540 | Vendors | 2017-07-10 | Architectural | 2019-01-01
9 | 270 | Vendors | 2018-04-06 | Cabling | 2019-01-01
9 | 270 | Vendors | 2018-04-06 | Telephone/data (POTS, T‐1, ISDN, DSL) | 2019-01-01
9 | 270 | Vendors | 2018-04-06 | Network (upgrade, back up, prepare for move) | 2019-01-01
9 | 270 | Vendors | 2018-04-06 | Security system | 2019-01-01
4 | 120 | Vendors | 2018-09-03 | Secure document destruction and removal | 2019-01-01
3 | 90 | Vendors | 2018-10-03 | Janitorial | 2019-01-01
3 | 90 | Vendors | 2018-10-03 | Plant watering | 2019-01-01
3 | 90 | Vendors | 2018-10-03 | Vending | 2019-01-01
3 | 90 | Vendors | 2018-10-03 | Courier | 2019-01-01
Please call Kevin Stringer with any questions at (916) 275-4447 or email at kstringer@chipmanrelo.com
Formulas:
TARGET COMPLETION = [TASK START]+B12